## Sheet1
col_0 | col_1 | col_2 | col_3 | col_4 | col_5 | col_6 | col_7 | col_8 | col_9 | col_10 | col_11 | col_12 | col_13 | col_14 | col_15 | col_16 | col_17 | col_18 | col_19 | col_20 | col_21 | col_22 | col_23 | col_24 | col_25 | col_26 | col_27 | col_28 | col_29 | col_30 | col_31 | col_32 | col_33 | col_34 | col_35 | col_36 | col_37 | col_38 | col_39 | col_40 | col_41 | col_42 | col_43 | col_44 | col_45 | col_46 | col_47 | col_48 | col_49 | col_50 | col_51 | col_52 | col_53 | col_54
Summary | Issue key | Issue id | Parent id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project description | Project url | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Resolved | Due Date | Votes | Labels | Labels | Description | Watchers | Watchers | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | 危 Original Estimate | 危 Remaining Estimate | 危 Time Spent | Security Level | Attachment | Custom field (Account) | Custom field (Business Value) | Custom field (Epic Color) | Custom field (Epic Link) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Iteration) | Custom field (Parent Link) | Custom field (Raised During) | Custom field (Rank) | Sprint | Custom field (Story Points) | Custom field (T-sizing) | Custom field (Team) | Custom field (Test Sessions) | Custom field (Testing Status) | Custom field ([CHART] Date of First Response) | Comment
SGP-6947: SG - HL - DMS - Discount | SGP-7458 | 26532 | 26231 | Sub-task | Open | SGP | Singapore | software | markvanderploeg |  |  | Maintenance |  | Zhang Kaijun | JailuLi | JailuLi | 42625.6625 | 42625.7256944444 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi | [19 empty] | 1¦i00dnt: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
TH - Prefill - AXA travel | SGP-7457 | 26531 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.65625 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  |  | JailuLi |  | 28800 | 28800 |  | 0 | 28800 | 28800 | [12 empty] | 1¦i00dnl: | Sprint 6.8 - Team 1 | 8 |  |  |  | Not started
TH - Prefill - Silkspan car | SGP-7456 | 26530 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.6555555556 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  |  | JailuLi |  | 57600 | 57600 |  | 0 | 57600 | 57600 | [12 empty] | 1¦i00dnd: | Sprint 6.8 - Team 1 | 16 |  |  |  | Not started
T1 - Team service - Jailu & Yanping | SGP-7441 | 26515 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.56875 | 42625.65625 | 42625.65625 |  |  | 0 |  |  |  | JailuLi |  | 57600 | 57600 |  | 0 | 57600 | 57600 | [12 empty] | 1¦i00dkh: | Sprint 6.8 - Team 1 | 16 |  |  |  | Not started
T1 - Knowledge sharing - Mock data in front-end | SGP-7440 | 26514 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.5680555556 | 42625.5694444444 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 28800 | 28800 |  | 0 | 28800 | 28800 | [12 empty] | 1¦i00dk9: | Sprint 6.8 - Team 1 | 8 |  |  |  | Not started
HTML - Create Environment of AngularJS | SGP-7439 | 26513 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  | Ywenbin | Ywenbin | Ywenbin | 42625.5680555556 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  |  | Ywenbin |  | 43200 | 43200 |  | 0 | 43200 | 43200 | [12 empty] | 1¦i00dk1: | Sprint 6.8 - Team 1 | 12 |  |  |  | Not started
HTML - Testing - SG - HL - full site adjustement | SGP-7438 | 26512 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  | Ywenbin | Ywenbin | Ywenbin | 42625.5673611111 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  |  | Ywenbin |  | 100800 | 100800 |  | 0 | 100800 | 100800 | [12 empty] | 1¦i00djt: | Sprint 6.8 - Team 1 | 28 |  |  |  | Not started
SG - HL - Detail page - Selenium | SGP-7428 | 26502 | 26475 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.4930555556 | 42625.5861111111 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 43200 | 43200 |  | 0 | 43200 | 43200 | [12 empty] | 1¦i00di9: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Detail page - Mobile view | SGP-7427 | 26501 | 26475 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.4930555556 | 42625.5847222222 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 36000 | 36000 |  | 0 | 36000 | 36000 | [12 empty] | 1¦i00di1: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Detail page - Desktop view | SGP-7426 | 26500 | 26475 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.4930555556 | 42625.5833333333 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 50400 | 50400 |  | 0 | 50400 | 50400 | [12 empty] | 1¦i00dht: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Detail page - Monthly payment API | SGP-7424 | 26498 | 26475 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.4923611111 | 42625.5 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 46800 | 46800 |  | 0 | 46800 | 46800 | [12 empty] | 1¦i00dhd: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Detail page - Detail API | SGP-7423 | 26497 | 26475 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.4923611111 | 42625.4951388889 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 57600 | 57600 |  | 0 | 57600 | 57600 | [12 empty] | 1¦i00dh5: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
Selenium enhanement - PageObject - Sample code | SGP-7418 | 26492 |  | Task | In Progress | SGP | Singapore | software | markvanderploeg |  |  | Minor |  | Zhiqiang | JailuLi | JailuLi | 42625.4680555556 | 42625.7277777778 | 42625.7243055556 |  |  | 0 |  |  | * SG - HL - Quotes page | JailuLi |  | 21600 | 21600 |  | 0 | 21600 | 21600 | [12 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyvm | Sprint 6.8 - Team 1 | 6 |  |  |  | Not started
SG - HL - Quotes page - Selenium | SGP-7412 | 26486 | 26474 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.4625 | 42625.4659722222 | 42625.7354166667 |  |  | 0 |  |  | * Windows 10 + Chrome * Grid + list view | JailuLi |  | 72000 | 72000 |  | 0 | 72000 | 72000 | [12 empty] | 1¦i00dex: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Quotes page - Mobile view | SGP-7408 | 26482 | 26474 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.45625 | 42625.4625 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 43200 | 43200 |  | 0 | 43200 | 43200 | [12 empty] | 1¦i00de1: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Quotes page - List view | SGP-7407 | 26481 | 26474 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.45625 | 42625.4618055556 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 43200 | 43200 |  | 0 | 43200 | 43200 | [12 empty] | 1¦i00ddt: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Quotes page - Grid view | SGP-7406 | 26480 | 26474 | Sub-task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | JailuLi | JailuLi | 42625.4555555556 | 42625.4611111111 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 64800 | 64800 |  | 0 | 64800 | 64800 | [12 empty] | 1¦i00ddl: | Sprint 6.8 - Team 1 |  |  |  |  | Not started
SG - HL - Detail page | SGP-7401 | 26475 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Major |  |  | JailuLi | JailuLi | 42625.4444444444 | 42625.6173611111 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 234000 | 234000 |  | 0 | 468000 | 468000 | [12 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyy | Sprint 6.8 - Team 1 | 65 |  |  |  | Not started
SG - HL - Quotes page | SGP-7400 | 26474 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Major |  |  | JailuLi | JailuLi | 42625.4430555556 | 42625.4722222222 | 42625.7354166667 |  |  | 0 |  |  |  | JailuLi |  | 223200 | 223200 |  | 0 | 446400 | 446400 | [12 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyxi | Sprint 6.8 - Team 1 | 62 |  |  |  | Not started
SG - HL - Form fill & edit detail | SGP-7399 | 26473 |  | Task | In Progress | SGP | Singapore | software | markvanderploeg |  |  | Major |  | Wenjie | JailuLi | JailuLi | 42625.4430555556 | 42625.7319444444 | 42625.725 |  |  | 0 |  |  | * API * Unit test * Manual test * Selenium adjustment | JailuLi | Wenjie | 72000 | 72000 |  | 0 | 72000 | 72000 | [12 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyx | Sprint 6.8 - Team 1 | 20 |  |  |  | Not started | 42625.7296873727 | 12/Sep/16 5:30 PM;Wenjie;* API - done * Unit test - in progress
Jailu - Brainstorm meeting | SGP-7398 | 26472 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | suzy | suzy | 42625.3986111111 | 42625.7243055556 | 42625.7243055556 |  |  | 0 |  |  |  | suzy |  | 144000 | 144000 |  | 0 | 144000 | 144000 | [6 empty] | SGP-1452 | [5 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyvg | Sprint 6.8 - Team 1 | 40 |  |  |  | Not started
T1 - Unforeseen | SGP-7314 | 26323 |  | Task | Closed | SGP | Singapore | software | markvanderploeg |  |  | Minor | Done | JailuLi | suzy | suzy | 42621.6576388889 | 42625.7236111111 | 42625.7236111111 | 42625.7236111111 |  | 0 |  |  |  | suzy |  | 28800 | 28800 |  | 0 | 28800 | 28800 | [6 empty] | SGP-1452 | [5 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyv3 | Sprint 6.8 - Team 1 | 8 |  |  |  | Not started
T1 - Sprint 6.7 - Bugs and deployment | SGP-7289 | 26231 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | suzy | suzy | 42620.6770833333 | 42625.6631944444 | 42625.6840277778 |  |  | 0 |  |  |  | suzy | [13 empty] | SGP-1453 | [5 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyv2 | Sprint 6.8 - Team 1 | 8 |  |  |  | Not started
TH - Display Car Plans from TCAP | SGP-7288 | 26230 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | Wongkot | Wongkot | 42620.6631944444 | 42625.725 | 42625.725 |  |  | 0 |  |  | TH Website, Car Insurance, ANC Car Broker Details are in the EPIC | Wongkot |  | 28800 | 28800 |  | 0 | 28800 | 28800 | [12 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyvv9 | Sprint 6.8 - Team 1 | 8 | XS(0-10) |  |  | Not started
Scrum - Sprint grooming | SGP-7270 | 26212 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | suzy | suzy | 42620.49375 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  |  | suzy |  | 72000 | 72000 |  | 0 | 72000 | 72000 | [6 empty] | SGP-1454 | [5 empty] | 1¦i00ctf: | Sprint 6.8 - Team 1 | 20 |  |  |  | Not started
Scrum - Sprint retrospective meeting | SGP-7269 | 26211 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | suzy | suzy | 42620.4930555556 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  |  | suzy |  | 57600 | 57600 |  | 0 | 57600 | 57600 | [6 empty] | SGP-1454 | [5 empty] | 1¦i00ct7: | Sprint 6.8 - Team 1 | 16 |  |  |  | Not started
Scrum - Sprint review meeting | SGP-7268 | 26210 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | suzy | suzy | 42620.4930555556 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  |  | suzy |  | 57600 | 57600 |  | 0 | 57600 | 57600 | [6 empty] | SGP-1454 | [5 empty] | 1¦i00csz: | Sprint 6.8 - Team 1 | 16 |  |  |  | Not started
Scrum - Daily scrum meeting | SGP-7267 | 26209 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | suzy | suzy | 42620.4923611111 | 42625.725 | 42625.725 |  |  | 0 |  |  |  | suzy |  | 64800 | 64800 |  | 0 | 64800 | 64800 | [6 empty] | SGP-1454 | [5 empty] | 1¦i00csr: | Sprint 6.8 - Team 1 | 18 |  |  |  | Not started
Scrum - Sprint planning meeting | SGP-7266 | 26208 |  | Task | Closed | SGP | Singapore | software | markvanderploeg |  |  | Minor | Done | JailuLi | suzy | suzy | 42620.4916666667 | 42625.725 | 42625.725 | 42625.725 |  | 0 |  |  |  | suzy |  | 230400 | 230400 |  | 0 | 230400 | 230400 | [6 empty] | SGP-1454 | [5 empty] | 1¦i00csj: | Sprint 6.8 - Team 1 | 64 |  |  |  | Not started
SG - Premium Update ¦ BUPA Health Plans (Oct 2016) | SGP-7249 | 26106 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | Janice Lim | Janice Lim | 42615.5597222222 | 42625.725 | 42625.725 |  |  | 0 | T1 |  |  | Janice Lim |  | 57600 | 57600 |  | 0 | 57600 | 57600 | [12 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyvur | Sprint 6.8 - Team 1 | 16 | S(11-20) |  |  | Not started
MY - Time estimation for Home Loans | SGP-7125 | 25503 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | Janice Lim | Janice Lim | 42606.5194444444 | 42625.725 | 42625.725 |  |  | 0 | T1 |  | Please advise if possible to give the breakdown as part of sprint grooming. A very rough estimation is needed based on the differences between SG and MY. We will keep in mind on our end that the accuracy will be reduced due to the time constraint. | Janice Lim |  | 21600 | 21600 |  | 0 | 21600 | 21600 | [12 empty] | 1¦hzzhwn:ixy8zhmij6nkjzywt | Sprint 6.8 - Team 2 | 6 | M(21-40) |  |  | Not started
TH - Tenure Based Case Not Working | SGP-7051 | 25400 |  | Bug | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | Wongkot | Wongkot | 42600.5076388889 | 42625.725 | 42625.725 |  |  | 0 | T1 |  | TH PROD, Personal Loans, Personal Loans Form filled The pre-fill tenure value in the PL form filled is not the same as set in the DMS !image-2016-08-18-11-10-52-717.png¦thumbnail! | Wongkot |  | 21600 | 21600 |  | 0 | 21600 | 21600 |  |  | 18/Aug/16 12:10 PM;Wongkot;image-2016-08-18-11-10-52-717.png;https://woodpecker.atlassian.net/secure/attachment/24805/image-2016-08-18-11-10-52-717.png | [9 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyvwx | Sprint 6.8 - Team 1 | 6 | XS(0-10) |  |  | Not started
SG - HL - Historical Reference Rates | SGP-6879 | 25002 |  | Task | New | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | Janice Lim | Janice Lim | 42594.3944444444 | 42625.6173611111 | 42625.7354166667 |  |  | 0 | Roadmap | T1 | * Import the Historical Reference Rates into H-Loans DMS, file attached. * API * Unit test Refer to Section (g) of Confluence: https://woodpecker.atlassian.net/wiki/display/SGP/Home+Loans+DMS+Requirements | Janice Lim |  | 115200 | 115200 |  | 0 | 115200 | 115200 |  |  | 12/Aug/16 9:26 AM;Janice Lim;Historical Reference Rates.xlsx;https://woodpecker.atlassian.net/secure/attachment/24500/Historical+Reference+Rates.xlsx |  |  |  | SGP-5965 | [5 empty] | 1¦hzzhwn:ixy8zhmij6nkjzyxr | Sprint 6.8 - Team 1 | 32 |  |  |  | Not started
T1 - QA - Health - Data testing | SGP-6871 | 24925 |  | Task | Open | SGP | Singapore | software | markvanderploeg |  |  | Minor |  |  | suzy | suzy | 42593.7270833333 | 42625.7256944444 | 42625.7256944444 |  |  | 0 |  |  | * Test data * Test case * Test script * API testing Note: Only the main flow will be covered in current sprint. All the special rules will be covered in the coming sprints. | suzy |  | 144000 | 144000 |  | 0 | 144000 | 144000 | [6 empty] | SGP-1575 | [5 empty] | 1¦i00dkn: | Sprint 6.8 - Team 1 | 40 |  |  |  | Not started